## Sheet1
Urology Options appraisal scoring
Option 1 – Do nothing
Criterion | Indicators | Weighting (out of 5) | Risk Scoring | Weighted score | Score person 1 (Out of 5) | Person 2 | Person 3 | Comments
Strategic fit | How well does the project fit within the Organisational /Divisional Strategy? | 2 | 4 | 8 | 2 | 1 | 1 | Doesn’t fit the strategic direction. Would not integrate teams. Would not improve quality outputs to stay as is.
Clinical Risk/Safety | What is the level of clinical risk being addressed? | 5 | 6 | 30 | 1 | 3 | 2 | Mantains status-quo. Will not achieve improvements
Estates Risk | What is the level of estates risk being adressed? | 1 | 8 | 8 | 3 | 3 | 2 | Estate at AUH not good for outpatients. We would still be across three sites which isn't a good medium/long term options
Quality | How much does the project contribute to the patietn quality of care? | 3 | 5 | 15 | 2 | 1 | 2 | No expected improvements to opportunities for improvement
Financial | How likely is the project to be affordable/earn an acceptable rate of return | 4 | 6 | 24 | 2 | 2 | 2 | Duplicated kit. No cost savings made
|  |  | total | 85
Option 2 - All Inpatients based at the Royal, Outpatients based at Broadgreen & Aintree
Criterion | Indicators | Weighting (out of 5) | Risk Scoring (out of 5) | Weighted score | Score person 1 | person 2 | person 3 | Comments
Strategic fit | How well does the project fit within the Organisational /Divisional Strategy? | 2 | 9 | 18 | 3 | 3 | 3 | Meets some strategic objectives.
Clinical Risk/Safety | What is the level of clinical risk being addressed? | 5 | 9 | 45 | 3 | 3 | 3 | Staff would be across sites still. Wouldn’t help to improve pathways. Would be away from services we work with
Estates Risk | What is the level of estates risk being adressed? | 1 | 9 | 9 | 3 | 3 | 3 | AUH outpatients would need development. RLH could support model.
Quality | How much does the project contribute to the patient quality of care? | 3 | 9 | 27 | 3 | 3 | 3 | Continue as a three site model. Questionnable quality and patient experience. No continuity.
Financial | How likely is the project to be affordable/earn an acceptable rate of return | 4 | 8 | 32 | 3 | 2 | 3 | Keep duplication of kit. Not good financially. Wouldn't need estate amends in the interim.
|  |  | total | 131
Option 3 - Elective Inpatients at the Royal, Emergency Inpatients at Aintree, Outpatients at Broadgreen & Aintree
Criterion | Indicators | Weighting (out of 5) | Risk Scoring | Weighted score | Score Person 1 (Out of 5) | Person 2 | Person 3 | Comments
Strategic fit | How well does the project fit within the Organisational /Divisional Strategy? | 2 | 11 | 22 | 3 | 4 | 4 | Does meet some strategic aims of the trust. Division would support.
Clinical Risk/Safety | What is the level of clinical risk being addressed? | 5 | 6 | 30 | 2 | 2 | 2 | Some clinical risks are mitigated but being based across two sites for inpatients is not idea. Some benefits could be achieved. Volume based outcomes improve.
Estates Risk | What is the level of estates risk being adressed? | 1 | 7 | 7 | 3 | 2 | 2 | Little change to current estate occupany. AUH improvements still needed
Quality | How much does the project contribute to the patient quality of care? | 3 | 4 | 12 | 2 | 2 | 2 | Staff across sites not beneficial.
Financial | How likely is the project to be affordable/earn an acceptable rate of return | 4 | 7 | 28 | 3 | 2 | 2 | Existing estate used. Still would need to develop AUH estate as inadequart. Still costs in rotas and locums
|  |  | total | 99
Option 4 - All inpatients at the Royal, Outpatients at Aintree, Broadgreen Outpatients to new Royal
Criterion | Indicators | Weighting (out of 5) | Risk Scoring | Weighted score | Score Person 1 (Out of 5) | Person 2 | Person 3 | Comments
Strategic fit | How well does the project fit within the Organisational /Divisional Strategy? | 2 | 9 | 18 | 3 | 3 | 3 | Meeting most strategic objectives - quality and efficiencies more than anything. Does not meet hot/cold split
Clinical Risk/Safety | What is the level of clinical risk being addressed? | 5 | 13 | 65 | 5 | 4 | 4 | Equitable service can be achieved. 2 site model. Access for patients is good
Estates Risk | What is the level of estates risk being adressed? | 1 | 10 | 10 | 4 | 3 | 3 | Estate meets requirements but some limitations as RLH estate will not be owned, will need to be shared
Quality | How much does the project contribute to the patient quality of care? | 3 | 12 | 36 | 4 | 4 | 4 | single site so better for patient care. More travel needed from north liverpool. Still presence at AUH
Financial | How likely is the project to be affordable/earn an acceptable rate of return | 4 | 11 | 44 | 3 | 4 | 4 | good savings to be made. Investment needed at AUH
|  |  | total | 173
Option 5 - All Inpatients and Outpatients at New Royal
Criterion | Indicators | Weighting (out of 5) | Risk Scoring | Weighted score | Score Person 1 (Out of 5) | Person 2 | Person 3 | Comments
Strategic fit | How well does the project fit within the Organisational /Divisional Strategy? | 2 | 6 | 12 | 3 | 1 | 2 | doesn’t fit strategic aims does fit recommendations/ models for external organisations
Clinical Risk/Safety | What is the level of clinical risk being addressed? | 5 | 11 | 55 | 4 | 3 | 4 | good continuity of care on a single site. No presence on auh is not ideal and would pose a risk
Estates Risk | What is the level of estates risk being adressed? | 1 | 6 | 6 | 3 | 1 | 2 | estate at RLH cannot manage all outpatient activity without other service having to move out to elsewhere. Limited daycase facilities for additional work.
Quality | How much does the project contribute to the patient quality of care? | 3 | 12 | 36 | 4 | 4 | 4 | would benefit continuity of care. Removes all presence on auh site. more travel for north liverpool patients
Financial | How likely is the project to be affordable/earn an acceptable rate of return | 4 | 12 | 48 | 4 | 4 | 4 | good reduction in duplicated kit. Investment needed on rlh site to include all this activity
|  |  | total | 157
Option 6 - All Inpatients at Aintree, Outpatients at Broadgreen and Aintree
Criterion | Indicators | Weighting (out of 5) | Risk Scoring | Weighted score | Score Person 1 (Out of 5) | Person 2 | Person 3 | Comments
Strategic fit | How well does the project fit within the Organisational /Divisional Strategy? | 2 | 6 | 12 | 2 | 2 | 2 | would not be aligned to interdependant services. In keeping with centralisation of services.
Clinical Risk/Safety | What is the level of clinical risk being addressed? | 5 | 6 | 30 | 2 | 2 | 2 | risk around not being on same site as interdependant services
Estates Risk | What is the level of estates risk being adressed? | 1 | 3 | 3 | 1 | 1 | 1 | limited space to support on auh site. Not enough theatre capacity
Quality | How much does the project contribute to the patient quality of care? | 3 | 8 | 24 | 2 | 3 | 3 | single site for inpatients would be good but not achieveable. No presence on rlh site
Financial | How likely is the project to be affordable/earn an acceptable rate of return | 4 | 6 | 24 | 1 | 3 | 2 | some efficiencies expected. Rota tiering would need to be in place. Investment needed in auh
|  |  | total | 93
Option 7 - All Inpatients at Royal, development of Broadgreen Urology centre for outpatients
Criterion | Indicators | Weighting (out of 5) | Risk Scoring | Weighted score | Score Person 1 (Out of 5) | Person 2 | Person 3 | Comments
Strategic fit | How well does the project fit within the Organisational /Divisional Strategy? | 2 | 7 | 14 | 3 | 2 | 2 | not in line with objectives of the trust. No AUH presense here.
Clinical Risk/Safety | What is the level of clinical risk being addressed? | 5 | 12 | 45 | 3 | 3 | 3 | some volume outcomes - beneficial but no auh presense is risky
Estates Risk | What is the level of estates risk being adressed? | 1 | 4 | 4 | 1 | 1 | 2 | RLH estate good for numbers. BGH would need investment and building work to relocate AUH activity
Quality | How much does the project contribute to the patient quality of care? | 3 | 7 | 21 | 2 | 2 | 3 | outpatients away from inpatients does not support continuity of care. Some benefits of scale. Wouldn’t meet expected quality outputs
Financial | How likely is the project to be affordable/earn an acceptable rate of return | 4 | 7 | 28 | 2 | 3 | 2 | not financially good. Investment needed in BGH
|  |  | total | 112

## Sheet2
Option | Score | Rank
Option 4 | 173 | 1
Option 5 | 157 | 2
Option 2 | 131 | 3
Option 7 | 112 | 4
Option 3 | 99 | 5
Option 6 | 93 | 6
Option 1 | 85 | 7